## Onboarding Tasks Resources
Phase No. | Phase | Activity | Task | Resource | Status | Notes / Questions
1 | ONBOARDING ¦ Planning & Kick-off
1.1 | Planning
|  | Gather Documents & Historical Data | Prepare sample documents for Onboarding Train-the-Trainer Sessions: 1) Historical Data - content containing completed Historical Content and/or Question & Answer pairs; usually a past RFP with completed responses (docx or xlsx preferred). 2) Blank Questionnaire/Project - a blank RFP, RFI, or Questionnaire; usually an unanswered project (docx or xlsx preferred). 3) Word Template - if your team uses a branded Word document for your final submissions (docx required). Only needed to provide if this is applicable to your projects. | Help Center: Prep Content for Import
|  | Meeting: Kick-Off | The Kickoff meeting introduces the RFPIO Onboarding Consultant as the direct point of contact during implementation. The Onboarding Consultant will lead the strategic discussion to outline goals and provides an overview of the RFPIO onboarding process. | See Calendar Invite Agenda
|  | Define Ownership of RFPIO | Define Super Admin and Core Admin Team - responsible for RFPIO implementation and championing internal rollout of RFPIO. | Refer to Kickoff information
|  | Administration | Super Admin / Core Admin Team to review Organization Settings and User Management. | University: Administration
|  | Get Started in RFPIO | Begin learning in RFPIO. Follow resources in "Self-Guided Tour". | Help Center: Self-Guided Tour
1.2 | IT Configurations (as needed)
|  | Supported Browsers | Check with your IT if any additional set up is needed to navigate to RFPIO in your web browser. (i.e. Ability to access your instance, ability to upload documents to RFPIO, ability to downloaded documents from RFPIO). RFPIO supports most standard browsers. (Chrome is the recommended browser.) RFPIO can send system notifications to your email, i.e. assignment notifications, task reminders, newsletters, marketing communications, etc. | RFPIO App URL
|  | IT Configurations and Add-ons Set Up (if applicable) | Refer to the Kickoff deck to see available Integrations and Add-ons included in your package. Add your IT Admins as Admin Users in RFPIO. Coordinate with your IT to schedule configurations. | Help Center: Integrations
2 | ONBOARDING ¦ Application Training
2.1 | Answer Library & Content Management
|  | Answer Library & Content Management Prep | Required pre-work: 1) Send any required sample documents to your Onboarding Consultant. 2) Complete the Content Management Learning Path in RFPIO University. | University: Foundations of Content Management
|  | Meeting: Answer Library Basics & Content Management | During this training, your Onboarding Consultant will guide Core Admin Team through RFPIO Answer Library fundamentals. | See Calendar Invite Agenda
|  | Content Organization Regroup | Core Admin Team to meet internally to discuss content organization structure. Leverage the "Content Organization - Worksheet (Excel)" to begin planning your content strategy. | Download: Content Organization - Worksheet (Excel)
2.2 | Project Management
|  | Project Management Prep | Required pre-work: 1) Send any required sample documents to your Onboarding Consultant. 2) Complete the Project Management Learning Path in RFPIO University. | University: Foundations of Project Management
|  | Meeting: Project Lifecycle | During this training, your Onboarding Consultant will guide Core Admin Team through RFPIO Projects fundamentals. | See Calendar Invite Agenda
|  | Project Workflow Regroup | Core Admin Team to meet internally to discuss project management strategy. Leverage the "Project Workflow - Worksheet (Excel)" to begin planning your project workflow. | Download: Project Workflow - Worksheet (Excel)
|  | Test Projects | Run test projects in RFPIO to solidify workflow. | Help Center: Projects Training Slides (new UX)
2.3 | Additional Training
|  | Moderation | Complete the Moderation course in RFPIO University. Core Admin Team to discuss internally whether Moderation will be needed. Speak with your Onboarding Consultant on this topic. | University: Moderation
|  | Document Library | Begin uploading documents into the Document Library (as needed). | Help Center: Managing the Document Library
|  | Intake | Complete the Intake course in RFPIO University. Core Admin Team to discuss internally whether Moderation will be needed. Speak with your Onboarding Consultant on this topic. | University: Enabling and Managing Intake
|  | Standard Reporting | Review the Standard Reporting available in the application. | Help Center: Reporting in RFPIO
|  | Section Templates | Complete Section Templates module in RFPIO University, including Section Template creation, organization, and usage. | University: Introduction to Section Templates
|  | Response Templates | Review Response Templates resources. | RFPIO Live: Let's Talk Response Templates
|  | Meeting: Custom Templates (if applicable) | RFPIO will guide training on Section and Response Templates for projects. | See Calendar Invite Agenda
|  | Add Section Templates & Response Templates into RFPIO | Upload Response Templates and Section Templates into RFPIO (as needed). | Help Center: Response Templates
3 | IMPLEMENTATION ¦ Meet with your CSM
3.1 | Implementation Prep
|  | Implementation Workshop Prep | Required pre-work: 1) Be prepared to talk about your Content Organization structure and Project Workflow. 2) Send any questions to Onboarding Consultant prior to meeting. | RFPIO Live: Let's Talk Implementation
|  | Meeting: Implementation Workshop | In this meeting, you will be introduced to your Customer Success Manager. You will share plans around your implementation. This marks the end of the initial Onboarding Cycle, at which point you will engage directly with your Customer Success Manager, who will continue to provide best practices and answer any outstanding questions you have about rolling this out to your team for the long-term. | See Calendar Invite Agenda
3.2 | Launch
|  | Rollout RFPIO within your org! | Begin training specific Teams / Team Members. Leverage the pre-made PowerPoint deck in our Help Center to create your own internal training slides for your end-users. | Help Center: Train the Trainer PPT Deck
|  | Go-Live | Soft-launch or full Go-live within your organization. Pilot a project, or begin running live projects in RFPIO. We encourage listening in to our past Webinar to inspire some ideas: - Evaluate your current process for improvement. - Adhere to APMP best practices by taking advantage of more RFPIO features. - Evaluate how RFPIO can help teams from proposals, sales, presales, customer support, and IT improve responses and content over time. | Webinar: Scale your response management process
|  | Confirm integrations and add-on features are set up (if applicable) | Reach out to RFPIO Support team if Technical Assistance is required. | Contact Support
4 | IMPLEMENTATION ¦ Deployment & Adoption
4.1 | Continue Learning
|  | Meeting: Office Hours with CSM | Office Hours are provided to the Core Admin Team as recurring scheduled meeting times with CSM. Office Hours can be used to address general questions around the tool, as well as covering additional best practices. These sessions are highly recommended during the first 3 months of implementation. | Schedule meeting times with CSM
|  | RFPIO University and Help Center | Check out our RFPIO University for available courses. Browse the Help Center for additional resources. | RFPIO University
|  | Meeting: Flex Sessions | Flex Sessions are provided as additional Train-the-Trainer sessions led by the CSM. Flex Sessions are designed to promote continued learning in the application. These sessions are not mandatory, but are available to the Customer if preferred, or if recommended by your CSM. These sessions are only offered during the first year of onboarding. | Reach out to your CSM to coordinate any Flex Sessions
|  | Stay in the know! | In the Help Center, check out the Release Notes and Best Practices pages for all the latest about RFPIO. Be sure to sign up for our newsletters to stay up to date on RFPIO news, events, and announcements. Reach out to your CSM if you are not sure how to subscribe. | Product Release Notes
4.2 | Additional Support
|  | Meeting: Introduction to Account Manager - Account Review | Account Reviews are scheduled strategic meetings between the Customer and RFPIO. The CSM will introduce the RFPIO Account Manager, review progress toward goals, share any important release updates or valuable new features, and evaluate any gaps or additional needs. The Core Admin Team will join in this meeting, but it is encouraged to invite RFPIO Champions and Executive Sponsors as well. | CSM will coordinate this meeting
|  | Professional Services for your Additional Needs | If your team requires additional support and training throughout onboarding, our Professional Services team can offer implementation services. Ask your Onboarding Consultant or Customer Success Manager for more information. | Datasheet of Professional Services can be provided upon request